## PRODUCT BACKLOG
PRODUCT BACKLOG
ID | Feature | Category | Priority | Sprint 1 | Sprint 2 | Sprint 3
0 | Show in a bar chart the 5 neighborhoods with the biggest amount of bike containers |  | M
1 | Show in a line chart the amount of stolen bicycles per month. |  | M
2 | Show the amount of stolen bicycles and amount of installed bike containers per month given a specific neighborhood through a grouped bar chart. The neighborhood should be selected by the user. |  | M
3 | Show in two pie charts the distribution of most stolen bike brands and colors. |  | M
4 | Mobile only: Save the current location of your bike in the note app. Note : your application must be capable of writing the note without explicitly opening the note app |  | M
5 | Mobile only: Create a reminder/appointment in the agenda about when to pick up the bike from a specific location. The application must be capable of putting the appointment in the agenda without explicitly opening the agenda application. |  | M
6 | Show on a map the amount of thefts per neighbourhood, by coloring the neighbourhood differently (shades of red/orange/yellow/green) based on the thefts amount. The border between neighbourhoods must be (somehow) clear. |  | S
7 | Show the location and route indication to the closest bike container to the user, given his/her current position. |  | S
8 | Create and fill database |  | S
9 | Create and implement parser |  | S
10 | Create UML diagrams |  | M | X
11 | Create a main menu |  | M
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26

## SPRINT 1 BACKLOG
SPRINT 1 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
10 | As a developer I want to have UML diagrams of my code so that I can better understand the way it is (or should be) built. | M | 20 | #Make UML diagram draft #Digitalize the UML diagram #Convert digital UML diagram into code | #UML diagrams are finished and once checked by P.O or Tutor