## PRODUCT BACKLOG
PRODUCT BACKLOG
ID | Feature | Category | Priority | Sprint 1 | Sprint 2 | Sprint 3
0 | Show in a bar chart the 5 neighborhoods with the biggest amount of bike containers |  | M |  | X
1 | Show in a line chart the amount of stolen bicycles per month. |  | M |  | X
2 | Show the amount of stolen bicycles and amount of installed bike containers per month given a specific neighborhood through a grouped bar chart. The neighborhood should be selected by the user. |  | M |  | X
3 | Show in two pie charts the distribution of most stolen bike brands and colors. |  | M
4 | Mobile only: Save the current location of your bike in the note app. Note : your application must be capable of writing the note without explicitly opening the note app |  | M
5 | Mobile only: Create a reminder/appointment in the agenda about when to pick up the bike from a specific location. The application must be capable of putting the appointment in the agenda without explicitly opening the agenda application. |  | M
6 | Show on a map the amount of thefts per neighbourhood, by coloring the neighbourhood differently (shades of red/orange/yellow/green) based on the thefts amount. The border between neighbourhoods must be (somehow) clear. |  | S
7 | Show the location and route indication to the closest bike container to the user, given his/her current position. |  | S
8 | Create and fill database |  | S |  |  | X
9 | Create and implement parser |  | S |  |  | X
10 | Create UML diagrams |  | M | X
11 | Create a main menu |  | M |  | X
12 | Install Programs |  | M | X
13
14
15
16
17
18
19
20
21
22
23
24
25
26

## SPRINT 1 BACKLOG
SPRINT 1 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
10 | As a developer I want to have UML diagrams of my code so that I can better understand the way it is (or should be) built. | M | 20 | #Make UML diagram draft #Digitalize the UML diagram #Convert digital UML diagram into code | #UML diagrams are finished and once checked by P.O or Tutor
11 | As a developer I want to have access to all software necessary, so I can start developing the application. | M | 20 | #install Xamarin #updates. | #Xamarin is fully installed and working on all devices without any errors
12 | As a developer I want to be able to create and convert UML files so that I have a clear view of what's going on in the application | M | 3 | #Install Astah case tool | #Astah is installed and operational
13 | As a team we want a cooperative contract so that we have a clear set of rules on how to work together during the project. | M | 3 | #Create cooperative contract | #Contract is complete and everybody agress on its content.
14
15

## SPRINT 2 BACKLOG
SPRINT 2 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
0 | As a user I want to be able to see the neighbourhoods with the most amout of bicycle containers in a bar chart so I know where I have the best chance of finding an empty one. | M | 8 | # Make a button # Make a bar chart code #Request information from database #Draw a visual representation of a bar chart | # Button is displayed and functional # Bar chart is displayed and functional
1 | As a user I want to see in which neighbourhood the most amount of bikes are stolen in a linechart, so I know where it is safe to park my bike. | M | 8 | #Make a button #Make a line chart code #Request information from database #Draw a visual representation of a line char | # Button is displayed and functional # Line chart is displayed and functional
3 | As a user I want to see what color and what brand of bikes are stolen, so I know what kind of bike won´t be stolen. | M | 8 | #Make a button #Make a pie chart code #Request information from database #Draw a visual representation of a pie chart | # Button is displayed and functional # Pie chart is displayed and functional
11 | As a developer I want a main menu so that the users can navigate to the application more easily. | M | 3 | #Create main menu #Create buttons | # Main menu starts at startup # Buttons are displayed

## SPRINT 3 BACKLOG
SPRINT 3 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
0 | As a user I want to be able to see the neighbourhoods with the most amout of bicycle containers in a bar chart so I know where I have the best chance of finding an empty one. | M | 8 | # Make a button # Make a bar chart code #Request information from database #Draw a visual representation of a bar chart | # Button is displayed and functional # Bar chart is displayed and functional
1 | As a user I want to see in which neighbourhood the most amount of bikes are stolen in a linechart, so I know where it is safe to park my bike. | M | 8 | #Make a button #Make a line chart code #Request information from database #Draw a visual representation of a line char | # Button is displayed and functional # Line chart is displayed and functional
8 | As a developer I want a database that contains all the information from my datasets so that I can easily add, remove, change or filter the information that I need | M | 5 | #Set up database on server with PosgreSQL | #Database is functional (Ready to fill)
9 | As a developer I want to have a parser in my code so that I can easily collect data from the database and use it. | S | 3 | #Build parser #Fill database | # There is a parser that can fill an empty database with data. #Database is filled with 2 datasets
11 | As a developer I want a main menu so that the users can navigate to the application more easily. | M | 3 | #Create main menu #Create buttons | # Main menu starts at startup # Buttons are displayed